## Sheet1
Royal University of Phnom Penh | [6 empty] | Faculty of Engineering
Smart Pet Feeding
|  | To be completed by: |  | Deadline: |  | Highlight Activities
|  | Team 12 |  | 2023-04-03 |  | This Year [2023-2024]
Action | Responsible | Start Date | End Date | Budget | Status | Progress | Note
Week #1: Researching
Espressif ESP32S | Kimhour | 2023-02-06 | 2017-02-13 | None | Started | 100%
RFID + (ARDUINO) | Lymchhun | 2023-02-06 | 2017-02-13 | None | Started | 100%
Storing Data (Database) | Kimhour | 2023-02-06 | 2017-02-13 | None | Started | 100%
Discussing | Group | 2023-02-11 | 2023-02-11 | None | Started | 100% | We must meet up
Week #2: Buying Component
Digilent Stepper Motor | Kimhour | 2023-02-13 | 2023-02-20 | None | Not Started | 0%
ESP32-WROVER-IE | Kimhour | 2023-02-13 | 2023-02-20 | None | Started | 100%
SG90 Micro-servo motor | Kimhour | 2023-02-13 | 2023-02-20 | None | Started | 100%
Discussing | Group | 2023-02-18 | 2023-02-18 | None | Not Started | 0% | We must meet up
Week #3: Software Design
Mit app controller design | Lymchhun | 2023-02-20 | 2023-03-06 | None | Not Started | 0%
Circuit Design | Kimhour | 2023-02-20 | 2023-03-06 | None | Not Started | 0%
Database Design | Kimhour | 2023-02-20 | 2023-03-06 | None | Not Started | 0%
Body of the object design | Lymchhun | 2023-02-20 | 2023-03-06 | None | Not Started | 0%
Discussing | Group | 2023-03-04 | 2023-03-04 | None | Not Started | 0% | We must meet up
Week #11: Connecting
Mit app ft Esp32 | Kimhour | 2023-03-06 | 2023-03-13 | None | Not Started
Esp32 with database | Lymchhun | 2023-03-06 | 2023-03-13 | None | Not Started
Discussing | Group | 2023-03-11 | 2023-03-11 | None | Not Started |  | We must meet up
Week #12: Retesting
Application | Group | 2023-03-06 | 2023-03-13 | None | Not Started
Security | Group | 2023-03-06 | 2023-03-13 | None | Not Started
Database | Group | 2023-03-06 | 2023-03-13 | None | Not Started
Discussing | Group | 2023-03-11 | 2023-03-11 | None | Not Started |  | We must meet up
Week #13: Build
Hardware | Group | 2023-03-13 | 2023-03-20 | None | Not Started |  | Connecting all the part of hardware
Hardware | Group | 2023-03-13 | 2023-03-20 | None | Not Started
Hardware | Group | 2023-03-13 | 2023-03-20 | None | Not Started
Discussing | Group | 2023-03-18 | 2023-03-18 | None | Not Started |  | We must meet up
Week #14: System Testing
Hardware + Software | Group | 2023-03-20 | 2023-03-27 | None | Not Started |  | Testing the hardware and software
Hardware + Software | Group | 2023-03-20 | 2023-03-27 | None | Not Started
Hardware + Software | Group | 2023-03-20 | 2023-03-27 | None | Not Started
Discussing | Group | 2023-03-25 | 2023-03-25 | None | Not Started |  | We must meet up